## Main User Story
USER ID | USER STORY | PRIORITY | RISK | STORY POINTS
1 | As a Customer, I want to view my profile, so that I can verify my personal information. | Must do | Low | 2
2 | As a Customer, I want to create a support ticket, so that I can report a problem or request assistance. | Must do | Low | 3
3 | As a Customer, I want to view my support ticket status, so that I can track the progress of my issue. | Must do | Low | 2
4 | As a Customer, I want to view my interaction history, so that I can know the previous communication with the organization. | Should do | Moderate | 3
5 | As a Customer, I want to submit feedback and a rating, so that I can share my experience with the organization. | Should do | Low | 2
6 | As a Sales Executive, I want to create a customer profile, so that customer information can be maintained in the CRM. | Must do | Low | 3
7 | As a Sales Executive, I want to create and manage leads, so that I can track potential customers. | Must do | Moderate | 3
8 | As a Sales Executive, I want to assign and follow up leads, so that potential customers are handled properly. | Must do | Moderate | 3
9 | As a Sales Executive, I want to record customer interactions, so that communication history is maintained. | Must do | Low | 3
10 | As a Sales Executive, I want to convert a qualified lead into a customer, so that the customer's information can be managed in the CRM. | Must do | Moderate | 3
11 | As a Support Executive, I want to view assigned support tickets, so that I can work on customer issues. | Must do | Low | 2
12 | As a Support Executive, I want to assign and update ticket status, so that customer issues can be tracked properly. | Must do | Moderate | 3
13 | As a Support Executive, I want to record support interactions, so that customer service history is maintained. | Must do | Low | 2
14 | As a Support Executive, I want to resolve and close support tickets, so that completed issues are properly recorded. | Must do | Moderate | 3
15 | As a Support Executive, I want to view customer history before resolving an issue, so that I can provide better support. | Should do | Moderate | 3
16 | As a Manager, I want to view customer information and activity summaries, so that I can monitor customer relationships. | Must do | Low | 3
17 | As a Manager, I want to view lead and conversion reports, so that I can evaluate sales performance. | Must do | Moderate | 5
18 | As a Manager, I want to view support ticket trends, so that I can identify recurring customer issues. | Must do | Moderate | 5
19 | As a Manager, I want to analyze customer feedback and satisfaction, so that I can identify areas for improvement. | Must do | High | 5
20 | As a Manager, I want to generate customer insights and reports, so that I can make informed business decisions. | Should do | High | 5
21 | As an Administrator, I want to create and manage user accounts, so that authorized users can access the CRM. | Must do | Low | 3
22 | As an Administrator, I want to assign roles and permissions, so that users can access only the functions relevant to their roles. | Must do | Moderate | 3
23 | As an Administrator, I want to manage system configuration, so that the CRM can operate according to organizational requirements. | Must do | Moderate | 5
24 | As an Administrator, I want to maintain and manage CRM data, so that the system information remains accurate and organized. | Must do | Moderate | 3
25 | As an Administrator, I want to view system activity logs, so that I can monitor important user and system activities. | Should do | Moderate | 3

## User Story Sprint
USER ID | SPRINT | USER STORY | STORY POINTS | PRIORITY | RISK | USER ID on which dependant
21 | 1 | As an Administrator, I want to create and manage user accounts, so that authorized users can access the CRM. | 3 | Must do | Low
23 | 1 | As an Administrator, I want to manage system configuration, so that the CRM can operate according to organizational requirements. | 5 | Must do | Moderate
2 | 1 | As a Customer, I want to create a support ticket, so that I can report a problem or request assistance. | 3 | Must do | Low
6 | 1 | As a Sales Executive, I want to create a customer profile, so that customer information can be maintained in the CRM. | 3 | Must do | Low
7 | 1 | As a Sales Executive, I want to create and manage leads, so that I can track potential customers. | 3 | Must do | Moderate
SPRINT 1 TOTAL STORY POINTS |  |  | 17
22 | 2 | As an Administrator, I want to assign roles and permissions, so that users can access only the functions relevant to their roles. | 3 | Must do | Moderate | 21
24 | 2 | As an Administrator, I want to maintain and manage CRM data, so that the system information remains accurate and organized. | 3 | Must do | Moderate | 23
8 | 2 | As a Sales Executive, I want to assign and follow up leads, so that potential customers are handled properly. | 3 | Must do | Moderate | 7
9 | 2 | As a Sales Executive, I want to record customer interactions, so that communication history is maintained. | 3 | Must do | Low | 6
10 | 2 | As a Sales Executive, I want to convert a qualified lead into a customer, so that the customer's information can be managed in the CRM. | 3 | Must do | Moderate | 7
11 | 2 | As a Support Executive, I want to view assigned support tickets, so that I can work on customer issues. | 2 | Must do | Low | 2
SPRINT 2 TOTAL STORY POINTS |  |  | 17
25 | 3 | As an Administrator, I want to view system activity logs, so that I can monitor important user and system activities. | 3 | Should do | Moderate | 24
1 | 3 | As a Customer, I want to view my profile, so that I can verify my personal information. | 2 | Must do | Low | 6
3 | 3 | As a Customer, I want to view my support ticket status, so that I can track the progress of my issue. | 2 | Must do | Low | 2
4 | 3 | As a Customer, I want to view my interaction history, so that I can know the previous communication with the organization. | 3 | Should do | Moderate | 9
5 | 3 | As a Customer, I want to submit feedback and a rating, so that I can share my experience with the organization. | 2 | Should do | Low | 6
16 | 3 | As a Manager, I want to view customer information and activity summaries, so that I can monitor customer relationships. | 3 | Must do | Low | 9
12 | 3 | As a Support Executive, I want to assign and update ticket status, so that customer issues can be tracked properly. | 3 | Must do | Moderate | 11
SPRINT 3 TOTAL STORY POINTS |  |  | 18
18 | 4 | As a Manager, I want to view support ticket trends, so that I can identify recurring customer issues. | 5 | Must do | Moderate | 12
19 | 4 | As a Manager, I want to analyze customer feedback and satisfaction, so that I can identify areas for improvement. | 5 | Must do | High | 5
20 | 4 | As a Manager, I want to generate customer insights and reports, so that I can make informed business decisions. | 5 | Should do | High | 16
15 | 4 | As a Support Executive, I want to view customer history before resolving an issue, so that I can provide better support. | 3 | Should do | Moderate | 4
SPRINT 4 TOTAL STORY POINTS |  |  | 18
PRODUCT BACKLOG
13 | Product Backlog | As a Support Executive, I want to record support interactions, so that customer service history is maintained. | 2 | Must do | Low | 12
14 | Product Backlog | As a Support Executive, I want to resolve and close support tickets, so that completed issues are properly recorded. | 3 | Must do | Moderate | 13
17 | Product Backlog | As a Manager, I want to view lead and conversion reports, so that I can evaluate sales performance. | 5 | Must do | Moderate | 10

## Dependency Check
Serial No | USER STORY | DEPENDENCY
1 | 1 | 6
2 | 3 | 2
3 | 4 | 9
4 | 5 | 6
5 | 8 | 7
6 | 9 | 6
7 | 10 | 7
8 | 11 | 2
9 | 12 | 11
10 | 13 | 12
11 | 14 | 13
12 | 15 | 4
13 | 16 | 9
14 | 17 | 10
15 | 18 | 12
16 | 19 | 5
17 | 20 | 16
18 | 22 | 21
19 | 24 | 23
20 | 25 | 24