## User Story-Ex
B2C CRM / CEM — USER STORY EX
Final logically-correct, non-equal Sprint Plan
USER ID | SPRINT | USER STORY | STORY POINTS | PRIORITY | RISK | USER ID on which dependant
21 | Sprint 1 | As an Administrator, I want to create and manage user accounts, so that authorized users can access the CRM. | 3 | Must do | Low
23 | Sprint 1 | As an Administrator, I want to manage system configuration, so that the CRM can operate according to organizational requirements. | 5 | Must do | Moderate
2 | Sprint 1 | As a Customer, I want to create a support ticket, so that I can report a problem or request assistance. | 3 | Must do | Low
6 | Sprint 1 | As a Sales Executive, I want to create a customer profile, so that customer information can be maintained in the CRM. | 3 | Must do | Low
7 | Sprint 1 | As a Sales Executive, I want to create and manage leads, so that I can track potential customers. | 3 | Must do | Moderate
SPRINT 1 TOTAL STORY POINTS |  |  | 17
USER ID | SPRINT | USER STORY | STORY POINTS | PRIORITY | RISK | USER ID on which dependant
22 | Sprint 2 | As an Administrator, I want to assign roles and permissions, so that users can access only the functions relevant to their roles. | 3 | Must do | Moderate | 21
24 | Sprint 2 | As an Administrator, I want to maintain and manage CRM data, so that the system information remains accurate and organized. | 3 | Must do | Moderate | 23
8 | Sprint 2 | As a Sales Executive, I want to assign and follow up leads, so that potential customers are handled properly. | 3 | Must do | Moderate | 7
9 | Sprint 2 | As a Sales Executive, I want to record customer interactions, so that communication history is maintained. | 3 | Must do | Low | 6
10 | Sprint 2 | As a Sales Executive, I want to convert a qualified lead into a customer, so that the customer's information can be managed in the CRM. | 3 | Must do | Moderate | 7
11 | Sprint 2 | As a Support Executive, I want to view assigned support tickets, so that I can work on customer issues. | 2 | Must do | Low | 2
SPRINT 2 TOTAL STORY POINTS |  |  | 17
USER ID | SPRINT | USER STORY | STORY POINTS | PRIORITY | RISK | USER ID on which dependant
25 | Sprint 3 | As an Administrator, I want to view system activity logs, so that I can monitor important user and system activities. | 3 | Should do | Moderate | 24
1 | Sprint 3 | As a Customer, I want to view my profile, so that I can verify my personal information. | 2 | Must do | Low | 6
3 | Sprint 3 | As a Customer, I want to view my support ticket status, so that I can track the progress of my issue. | 2 | Must do | Low | 2
4 | Sprint 3 | As a Customer, I want to view my interaction history, so that I can know the previous communication with the organization. | 3 | Should do | Moderate | 9
5 | Sprint 3 | As a Customer, I want to submit feedback and a rating, so that I can share my experience with the organization. | 2 | Should do | Low | 6
16 | Sprint 3 | As a Manager, I want to view customer information and activity summaries, so that I can monitor customer relationships. | 3 | Must do | Low | 9
12 | Sprint 3 | As a Support Executive, I want to assign and update ticket status, so that customer issues can be tracked properly. | 3 | Must do | Moderate | 11
SPRINT 3 TOTAL STORY POINTS |  |  | 18
USER ID | SPRINT | USER STORY | STORY POINTS | PRIORITY | RISK | USER ID on which dependant
18 | Sprint 4 | As a Manager, I want to view support ticket trends, so that I can identify recurring customer issues. | 5 | Must do | Moderate | 12
19 | Sprint 4 | As a Manager, I want to analyze customer feedback and satisfaction, so that I can identify areas for improvement. | 5 | Must do | High | 5
20 | Sprint 4 | As a Manager, I want to generate customer insights and reports, so that I can make informed business decisions. | 5 | Should do | High | 16
15 | Sprint 4 | As a Support Executive, I want to view customer history before resolving an issue, so that I can provide better support. | 3 | Should do | Moderate | 4
SPRINT 4 TOTAL STORY POINTS |  |  | 18
PRODUCT BACKLOG
USER ID | SPRINT | USER STORY | STORY POINTS | PRIORITY | RISK | USER ID on which dependant
13 | Product Backlog | As a Support Executive, I want to record support interactions, so that customer service history is maintained. | 2 | Must do | Low | 12
14 | Product Backlog | As a Support Executive, I want to resolve and close support tickets, so that completed issues are properly recorded. | 3 | Must do | Moderate | 13
17 | Product Backlog | As a Manager, I want to view lead and conversion reports, so that I can evaluate sales performance. | 5 | Must do | Moderate | 10

## Main User Story
USER ID | ACTOR | USER STORY | STORY POINTS | PRIORITY | RISK
1 | Customer | As a Customer, I want to view my profile, so that I can verify my personal information. | 2 | Must do | Low
2 | Customer | As a Customer, I want to create a support ticket, so that I can report a problem or request assistance. | 3 | Must do | Low
3 | Customer | As a Customer, I want to view my support ticket status, so that I can track the progress of my issue. | 2 | Must do | Low
4 | Customer | As a Customer, I want to view my interaction history, so that I can know the previous communication with the organization. | 3 | Should do | Moderate
5 | Customer | As a Customer, I want to submit feedback and a rating, so that I can share my experience with the organization. | 2 | Should do | Low
6 | Sales Executive | As a Sales Executive, I want to create a customer profile, so that customer information can be maintained in the CRM. | 3 | Must do | Low
7 | Sales Executive | As a Sales Executive, I want to create and manage leads, so that I can track potential customers. | 3 | Must do | Moderate
8 | Sales Executive | As a Sales Executive, I want to assign and follow up leads, so that potential customers are handled properly. | 3 | Must do | Moderate
9 | Sales Executive | As a Sales Executive, I want to record customer interactions, so that communication history is maintained. | 3 | Must do | Low
10 | Sales Executive | As a Sales Executive, I want to convert a qualified lead into a customer, so that the customer's information can be managed in the CRM. | 3 | Must do | Moderate
11 | Support Executive | As a Support Executive, I want to view assigned support tickets, so that I can work on customer issues. | 2 | Must do | Low
12 | Support Executive | As a Support Executive, I want to assign and update ticket status, so that customer issues can be tracked properly. | 3 | Must do | Moderate
13 | Support Executive | As a Support Executive, I want to record support interactions, so that customer service history is maintained. | 2 | Must do | Low
14 | Support Executive | As a Support Executive, I want to resolve and close support tickets, so that completed issues are properly recorded. | 3 | Must do | Moderate
15 | Support Executive | As a Support Executive, I want to view customer history before resolving an issue, so that I can provide better support. | 3 | Should do | Moderate
16 | Manager | As a Manager, I want to view customer information and activity summaries, so that I can monitor customer relationships. | 3 | Must do | Low
17 | Manager | As a Manager, I want to view lead and conversion reports, so that I can evaluate sales performance. | 5 | Must do | Moderate
18 | Manager | As a Manager, I want to view support ticket trends, so that I can identify recurring customer issues. | 5 | Must do | Moderate
19 | Manager | As a Manager, I want to analyze customer feedback and satisfaction, so that I can identify areas for improvement. | 5 | Must do | High
20 | Manager | As a Manager, I want to generate customer insights and reports, so that I can make informed business decisions. | 5 | Should do | High
21 | Administrator | As an Administrator, I want to create and manage user accounts, so that authorized users can access the CRM. | 3 | Must do | Low
22 | Administrator | As an Administrator, I want to assign roles and permissions, so that users can access only the functions relevant to their roles. | 3 | Must do | Moderate
23 | Administrator | As an Administrator, I want to manage system configuration, so that the CRM can operate according to organizational requirements. | 5 | Must do | Moderate
24 | Administrator | As an Administrator, I want to maintain and manage CRM data, so that the system information remains accurate and organized. | 3 | Must do | Moderate
25 | Administrator | As an Administrator, I want to view system activity logs, so that I can monitor important user and system activities. | 3 | Should do | Moderate

## Actor Summary
Actor | Number of User Stories
Customer | 5
Sales Executive | 5
Support Executive | 5
Manager | 5
Administrator | 5

## Legend
Field | Meaning
User Story | As a [Actor], I want to [Action], so that [Benefit].
Story Points | Relative effort/complexity, not hours.
Priority | Must do / Should do / Could do.
Risk | Low / Moderate / High.
Total Actors | 5
Total User Stories | 25

## Sprint Summary
SPRINT | NUMBER OF STORIES | STORY POINTS
Sprint 1 | 5 | 17
Sprint 2 | 6 | 17
Sprint 3 | 7 | 18
Sprint 4 | 4 | 18

## Dependency Check
USER STORY | DEPENDENCY | STATUS
1 | 6 | Correct
2 |  | Independent
3 | 2 | Correct
4 | 9 | Correct
5 | 6 | Correct
6 |  | Independent
7 |  | Independent
8 | 7 | Correct
9 | 6 | Correct
10 | 7 | Correct
11 | 2 | Correct
12 | 11 | Correct
13 | 12 | Product Backlog
14 | 13 | Product Backlog
15 | 4 | Correct
16 | 9 | Correct
17 | 10 | Product Backlog
18 | 12 | Correct
19 | 5 | Correct
20 | 16 | Correct
21 |  | Independent
22 | 21 | Correct
23 |  | Independent
24 | 23 | Correct
25 | 24 | Correct